## Risk Register
ISO 27001:2022 — IT Risk Register
Inherent & Residual Risk Scoring · Likelihood × Impact Matrix
TOTAL RISKS |  | CRITICAL |  | HIGH |  | AVG RISK REDUCTION |  | OPEN TREATMENTS |  | OVERDUE
6 |  | 0 |  | 0 |  | 48.6% |  | 4 |  | 0
Risk ID | Category | Asset / Process | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Rating | Existing Controls | Control Effectiveness | Residual Score | Residual Rating | Risk Reduction % | Treatment | Status | Owner | Due Date | Notes
R-001 | Cybersecurity | Email System | Phishing / BEC Attack | Lack of DMARC & advanced email filtering | 4 | 5 | 20 | Critical | DMARC, SPF, DKIM deployed; Defender for Office 365 | High | 6 | Medium | 70 | Implement Defender for O365 Plan 2 + Awareness Training | Open | Krishnaprabu | 2025-03-31 | Linked to M365 hardening project
R-002 | Cloud Security | Azure Subscriptions | Misconfigured cloud storage | Public blob containers, no CSPM | 3 | 4 | 12 | High | Azure Policy enforcing no-public-blob | Medium | 6 | Medium | 50 | Enable Defender for Storage + Blob Policy | In Progress | Cloud Team | 2025-04-15 | Terraform IaC deployment pending
R-003 | Access Control | Active Directory | Privilege escalation | Excessive admin accounts, no PAM | 3 | 5 | 15 | High | AD hardening applied, Ansible playbook | Medium | 6.75 | Medium | 55 | Deploy PAM solution; enforce tiered admin model | Open | IT Security | 2025-05-01 | AD Hardening Ansible project addresses this
R-004 | Data Protection | Customer Database | Ransomware / data encryption | No immutable backups; flat network | 4 | 5 | 20 | Critical | Daily backups to Azure Blob | Low | 12 | High | 40 | Implement immutable backup vault + network segmentation | Open | IT Manager | 2025-03-15 | CRITICAL — prioritise immediately
R-005 | Compliance | ISMS Documentation | Audit non-conformity | Incomplete records and undocumented controls | 2 | 4 | 8 | Medium | Policy library maintained in SharePoint | High | 2.8 | Low | 65 | Complete SoA update; schedule internal audit | In Progress | ISMS Lead | 2025-04-30 | ISO 27001 Stage 2 audit Q3 2025
R-006 | Third Party | Cloud Providers | Third-party data breach | Inadequate supplier security assessments | 3 | 4 | 12 | High | Vendor questionnaires in place | Medium | 6.6 | Medium | 45 | Implement formal TPCRM programme | Open | Procurement | 2025-06-01 | Annex A 5.19-5.22 control area
R-007 | Human Risk | All Staff | Social engineering / insider threat | No security awareness programme | 4 | 4 | 16 | High | Annual security training | Low | 8 | Medium | 50 | Quarterly phishing simulations + role-based training | In Progress | HR / Security | 2025-03-31 | Phishing toolkit project aligned
R-008 | Network Security | Corporate Network | Lateral movement post-breach | Flat network; no micro-segmentation | 3 | 5 | 15 | High | Firewall at perimeter | Low | 9 | Medium | 40 | Zero Trust architecture via Azure Firewall + segmentation | Open | Network Team | 2025-05-30 | Zero Trust Terraform project addresses this
R-009 | Business Continuity | Critical Applications | Extended system downtime | No tested DR plan; single region | 3 | 5 | 15 | High | Some manual failover procedures | Low | 8.25 | Medium | 45 | Design & test multi-region DR with RTO < 4 hours | Open | IT Manager | 2025-07-01 | BCP/DRP review scheduled Q2 2025
R-010 | Vulnerability Mgmt | All Systems | Unpatched critical vulnerability exploitation | No automated patch management | 3 | 4 | 12 | High | Monthly manual patching | Medium | 5.4 | Low | 55 | Deploy Microsoft Intune autopatch + Qualys scanning | In Progress | IT Operations | 2025-04-15 | Aligned to DevSecOps pipeline project

## ISO27001 Gap Analysis
ISO 27001:2022 — Gap Analysis (All 93 Controls)
Annex A Control Assessment · Score 0=Not Implemented · 5=Fully Implemented
Control ID | Domain | Control Title | Description | Current Maturity (0-5) | Target Maturity | Gap | Implementation Status | Evidence | Priority | Owner | Target Date | Notes
5.1 | Org Controls | Policies for information security | IS policy reviewed annually and communicated | 4 | 5 | 3 | Partially Implemented | IS Policy v3.2 in SharePoint | High | ISMS Lead | 2025-Q2 | Needs board sign-off on latest revision
5.2 | Org Controls | Information security roles | Roles defined in RACI matrix | 3 | 5 | 3 | Partially Implemented | RACI document v1.1 | High | CISO | 2025-Q1 | Security champion programme needed
5.14 | Org Controls | Information transfer | Data classification & transfer controls | 2 | 4 | 4 | Not Implemented | Draft policy only | High | Legal/IT | 2025-Q2 | UAE PDPL compliance required
5.19 | Org Controls | Information security in supplier relationships | Vendor assessment questionnaire | 3 | 5 | 3 | Partially Implemented | 25 of 40 vendors assessed | High | Procurement | 2025-Q3 | TPCRM programme in development
6.1 | People Controls | Screening | Background checks for all staff | 4 | 5 | 2 | Mostly Implemented | HR pre-employment policy | Medium | HR | 2025-Q2 | Contractor screening gaps
6.3 | People Controls | Information security awareness | Annual training only | 2 | 5 | 4 | Not Implemented | LMS records 2024 | High | HR/Security | 2025-Q1 | Phishing simulation programme needed
7.1 | Physical Controls | Physical security perimeters | Datacentre physical access controls | 5 | 5 | 0 | Fully Implemented | CCTV, badge access, mantrap | Low | Facilities | N/A | Compliant — evidence on file
7.4 | Physical Controls | Physical security monitoring | 24/7 CCTV, guard rounds | 5 | 5 | 0 | Fully Implemented | Security monitoring SOPs | Low | Facilities | N/A | Annual review completed
8.2 | Tech Controls | Privileged access rights | Privileged accounts reviewed quarterly | 3 | 5 | 3 | Partially Implemented | AD access reviews Q4 2024 | High | IT Admin | 2025-Q1 | PAM solution required
8.5 | Tech Controls | Secure authentication | MFA enforced on all SaaS and email | 4 | 5 | 2 | Mostly Implemented | Entra ID MFA report | High | IT Security | 2025-Q1 | Legacy apps still use passwords
8.7 | Tech Controls | Protection against malware | Defender for Endpoint deployed | 4 | 5 | 2 | Mostly Implemented | Defender coverage report | Medium | IT Security | 2025-Q1 | 100% coverage target
8.8 | Tech Controls | Management of technical vulnerabilities | Monthly scanning partial | 2 | 5 | 4 | Not Implemented | Nessus scan Q3 2024 | High | IT Ops | 2025-Q2 | Automated patch management needed
8.12 | Tech Controls | Data leakage prevention | No DLP implemented | 1 | 4 | 4 | Not Implemented | None | High | CISO | 2025-Q3 | Microsoft Purview DLP planned
8.15 | Tech Controls | Logging | SIEM with Sentinel deployed | 4 | 5 | 2 | Mostly Implemented | Sentinel workspace active | High | SOC | 2025-Q1 | Alert tuning in progress
8.23 | Tech Controls | Web filtering | Defender for Endpoint + proxy | 4 | 5 | 2 | Mostly Implemented | Web filter policy active | Medium | IT Ops | 2025-Q2 | Category review needed
8.24 | Tech Controls | Use of cryptography | Encryption at rest and in transit | 4 | 5 | 2 | Mostly Implemented | BitLocker, TLS 1.2/1.3 | Medium | IT Security | 2025-Q1 | Key management review due
8.28 | Tech Controls | Secure coding | DevSecOps pipeline planned | 2 | 5 | 4 | Not Implemented | Pipeline template in dev | High | DevOps | 2025-Q2 | Aligned to DevSecOps project
8.30 | Tech Controls | Outsourced development | Vendor code review process | 1 | 4 | 4 | Not Implemented | None | High | IT/Legal | 2025-Q3 | Policy needed

## Dashboard
ISMS Executive Dashboard
TOTAL CONTROLS ASSESSED |  | FULLY IMPLEMENTED | PARTIALLY IMPLEMENTED | NOT IMPLEMENTED | CRITICAL RISKS
18 |  | 2 | 4 | 6 | 2
Risk Summary by Category
Category | Count | Critical+High
Cybersecurity | 1 | 1
Cloud Security | 1 | 1
Access Control | 1 | 1
Data Protection | 1 | 1
Compliance | 1 | 0
Third Party | 1 | 1
Human Risk | 1 | 1
Network Security | 1 | 1
Business Continuity | 1 | 1
Vulnerability Mgmt | 1 | 1